# Westport Lions Santa Clause Parade Managers Guide

Created by the club, Marty Hawkins, B. Reddick & Michael Harris

## General

This guide was created from the experience of previous activity managers listed above who would be pleased to consult.  It is as the title suggests, a guide not a rule book.  The manager for the year will have to use their judgement on all matters considering the prevailing conditions for that year and other factors which can change from time to time.

The Westport Lions Santa Claus Parade is one of the major club events each year involving a great deal of organization but also a lot of help from the whole of the membership and volunteers.  A suggestion is included on how to divide up the various tasks under the Committee heading.

The Parade always takes place on the afternoon of the last Saturday of each November.  Under the Checklist heading suggested deadlines are included.

## Organization

One of the most important tasks of the activity manager is to assemble a committee of members and volunteers who will assist.  Below is a suggested list of responsibilities for each committee member.  The skeleton committee should be in place before the end of September with other members added as necessary.  Determine who is responsible for each item and when a task is to be complete.

### Committee

Sponsorship _______________________

Traffic control _______________________

Parade marshal _______________________

Advertising and Parade Brochure _______________________

Securing bands and floats _______________________

Santa and his sleigh____________________________

Food _______________________

## Things To Do Before the Parade

Obtain budget from club in September _______________________

Determine parade theme in September_______________________

Secure Esso/Circle K for marshalling in September_______________________

Secure Police for traffic control in September_______________________

Insurance?

Ask Ricki for permission to park on his lot in September_______________________

Check with village about street closures and parade route in October _______________________

Obtain sponsorship up to 10 days before parade_______________________

Secure fire departments in October_______________________

Confirm Santa in October _______________________

- Obtain candy for children (No Frills in Sept.) _______________________

- Decorate Santa’s float during week before parade.

- Confirm horses and wagon from Chris Hagan or Dale Lyons in October_______________________

- Obtain cutter from Dale Lyons in October_______________________

- Protection for Santa i.e. tent

Contact Mr. Wills about music from 10:00 – 2:00 p.m. in October __________________________

Advertising – Contact Lake 88, Ad in paper, website, FB in October _______________________

Let float participants know there is to be no Santas on floats _______________________

Ask float participants for clear signage to identify themselves _______________________

Brochure – List of sponsors and participants ready for printing 10 days before parade. _______________________

Judges for parade two weeks before parade _______________________

Director of Parade – (MC) in October_______________________

MC PA and arrangements.

Map of parade route, google maps, satellite picture of parade route for brochure_____________________

Food Bank wagon- driver and two helpers _______________________

Toy Drive wagon – driver and two helpers _______________________

Clowns? _______________________

Traffic Control Volunteers _______________________

Marshalling Helpers _______________________

Food Volunteers _______________________

Food __________________________

- Secure two BBQs,

- pot, and burner to boil wieners,

- drinks,

- buns,

- mustard relish,

- table, cups, drinks, hot chocolate _________________

- gloves, napkins, tongs,

- one person to serve hot chocolate, one person to open buns on tray, one person to serve hotdogs, one person to cook hotdogs,

Parade Marshal Assistants ________________________

Traffic Control Assistants __________________________

## On The Day

Marshalling

- establish one way and line ups at Circle K

- arrangements for dealing with horse manure

- Megaphone for parade marshal, Santa Claus

Traffic Control

- distribute barricades and pylons

- assign volunteers to each road junction

- establish communications

Brochure Distribution

Santa set up

Food set up.

MC set up.

## After Parade

Traffic barricades and pylons stored

Thank you, ad, for sponsors

Reflection on Parade – Things that went well, Improvements

Obtain plaques or gift certificates for Best float, Float closest to theme, Honourable mention and arrange presentation.